## Sayfa1
Task | Start Date | Days to Complete
Problem Definition and Requirements | 2020-02-10 | 14
RFID System | 2020-02-24 | 14
Door Side Functions | 2020-02-24 | 14
Face Recognition | 2020-03-09 | 10
Administrative Panel | 2020-03-09 | 14
Puppet Mechanical Design | 2020-03-23 | 10
Magic Mirror Production | 2020-03-23 | 10
Magic Mirror GUI | 2020-04-02 | 10
Puppet Electronic Design | 2020-04-02 | 14
Puppet Attribute Integration | 2020-04-16 | 15